## Project Plan
Virtual Arts - Technical Test
Project Plan
Note: Higher priority = more important
Task ID | Task Name | Estimated Task Duration (Hours) | Task Dependencies | Priority (?/10)
1 | Create project plan spreadsheet | 0.5 |  | 10
2 | Produce Gantt chart | 0.5 | 1 | 10
3 | Start project planning document | 0.5 |  | 8
4 | Populate Trello board | 0.5 | 1 | 10
5 | Obtain 3D model asset (with components) | 0.5 |  | 8
6 | Splash screen | 0.5 |  | 5
7 | Set up Unity project for AR and Android | 0.5 |  | 10
8 | Place object in scene using camera | 4 | 5, 7 | 9
9 | Rotate object in scene using swipe gesture | 4 | 8 | 7
10 | Pinch gesture to explode 3D model | 6 | 8 | 7
11 | Compile Calibration Scene | 1 | 9 | 8
12 | Compile Game Scene | 1 | 10 | 8
13 | Design UI | 1 |  | 5
14 | Implement UI | 1 | 13 | 5
15 | Create Android Build | 0.5 | 11, 12, 14 | 8
16 | Ensure application runs same in Unity as on mobile | 0.5 | 15 | 4
17 | Review code for iOS compatability | 1 | 15 | 3
18 | Test Android build | 1 | 15 | 6
19 | Final changes based on testing | 1 | 18 | 3
20 | Export final Android build | 0.5 | 19 | 8
21 | List suggested project improvements | 0.5 | 20 | 4
22 | Review and update project planning document | 0.5 | 21 | 2
23 | Collate build, source files and documents in ZIP file | 0.5 | 22 | 10
24 | Upload ZIP project to cloud storage | 0.5 | 23 | 10
25 | Create demo video of app | 1 | 19 | 1
26 | Upload demo video to YouTube as unlisted | 0.5 | 25 | 1
Total duration: 29.5 hours.

## Gantt Chart
Virtual Arts - Technical Test
Gantt Chart
Time (Hours)
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
[ID: 1] Create project plan spreadsheet
[ID: 2] Produce gantt chart
[ID: 4] Populate Trello board
[ID: 7] Set up Unity project for AR and android
[ID: 3] Start planning document
[ID: 5] Obtain 3D model asset
[ID: 8] Place object in scene using camera
[ID: 9] Rotate object in scene using swipe gesture
[ID: 11] Compile Calibration Scene
[ID: 10] Pinch gesture to explode 3D model
[ID: 12] Compile Game Scene
[ID: 13] Design UI
[ID: 14] Implement UI
[ID: 15] Create Android Build
Tasks | [ID: 18] Test Android Build
[ID: 6] Splash screen
[ID: 16] Ensure application runs same in Unity as on mobile
[ID: 17] Review code for iOS compatability
[ID: 19] Final changes based on testing
[ID: 20] Export final Android build
[ID: 21] List suggested project improvements
[ID: 22] Review and update project planning document
[ID: 23] Collate build, source files and documents in ZIP file
[ID: 24] Upload ZIP project to cloud storage
[ID: 25] Create demo video of app
[ID: 26] Upload demo video to YouTube as unlisted